## Executive
DOMAIN-ADAPTIVE FUSION — EXECUTIVE PLAN
Zero-label cross-system log anomaly detection ¦ HDFS/BGL are source domains, not the final target.
Total micro-tasks | 32 | Must tasks | 31 | Gates | 5 | Current state | P1 COMPLETE — no empirical result
Mục tiêu: model học knowledge đa kiến trúc nguồn, tự hiệu chỉnh bằng target normal buffer không nhãn, sau đó phát hiện anomaly với confidence/evidence và khả năng abstain.
Component | Role in final model | Target-label policy | Success evidence | Risk / guardrail | Owner | Phase | Status
Canonical view | Mask fields; retain raw text + optional template | Never used | Schema and leakage audit pass | Do not lose raw semantics | AI | P1 | Finished
Semantic expert | Llama-3.1-8B + LoRA-Semantic | Never used | Held-out target semantic AP/evidence | Vocabulary/format drift | AI | P2 | Planned
Sequence expert | LoRA-Sequence reference + required lighter sequence candidate; winner undecided | Never used | Per-target next-log evidence | Preserve explicit order/context; GTAT is not a substitute until tested | AI | P2 | Planned
Structural expert | Temporal Graph Transformer (GTAT) | Never used | FAR, drift and graph coverage | Missing topology metadata | AI | P2 | Planned
Adaptive gate | Weights experts by drift/uncertainty/coverage | Never used | Better stability than equal weights | Overfit to source architectures | AI + Researcher | P3 | Planned
Target adaptation | Learns normal baseline from burn-in buffer | Unlabeled buffer only | Calibration and contamination robustness | Insufficient/contaminated buffer | Researcher | P3–P4 | Planned

## Roadmap
4-PHASE ROADMAP
Each phase has an explicit exit gate. Empirical runs and final conclusions remain researcher-owned.
Phase | Timing | Objective | Micro-task count | Key outputs | Exit gate | Main risk | Owner | Status
P1 · Data & Protocol | W1–W2 | Create multi-source schema, target-buffer contract and leave-one-architecture-out evaluation. | 8 | Registry, unified schema, split manifests, leakage audit | G0: Protocol Ready | Target labels or mixed-domain leakage | AI + Researcher | Finished
P2 · Representation & Experts | W3–W4 | P2.PRE metadata freeze, semantic expert, sequence reference + lighter candidate, GTAT, evidence and diversity freeze. | 8 | LLM-BASE-001, semantic, two sequence candidates, GTAT, common evidence, diversity/freeze package | G2: Expert Diversity Ready | Adapters share weights or experts learn same shortcut | AI + Researcher | Planned
P3 · Adaptation & Fusion | W5–W6 | Calibrate target normal buffer; validate MLP 8→32→16→3 gate without target labels. | 8 | Target memory, drift/uncertainty, fusion gate, explanations | G3: Fusion Justified | Gate overfits source domains | AI + Researcher | Planned
P4 · Cross-System Validation | W7–W8 | Evaluate held-out architectures; test ablation, cold start and contamination; report evidence. | 8 | LOAO results, robustness, reproducibility bundle, report | G4: Final Evaluation | Overclaiming beyond evaluated domains | Researcher + AI | Planned

## Task Register
TASK REGISTER — DOMAIN-ADAPTIVE FUSION
32 micro-tasks ¦ status cells are editable; evidence must be traceable before a task is closed.
Task ID | Phase | Workstream | Class | Micro-task | Output | Owner | Timing | Dependency | Definition of Done | Status
P1.1 | P1 · Data & Protocol | Research scope | Must | Chốt định nghĩa source architecture, unseen target và zero-label target adaptation | Scope memo | Người nghiên cứu | Week 1 | — | Không còn claim chỉ HDFS/BGL; target labels bị cấm trong adaptation. | Done
P1.2 | P1 · Data & Protocol | Dataset portfolio | Must | Lập inventory ít nhất 3 source architectures và 1 held-out target mỗi fold | Dataset registry | AI + Người nghiên cứu | Week 1 | P1.1 | Mỗi dataset có licence, format, chronology và label availability rõ ràng. | Done
P1.3 | P1 · Data & Protocol | Canonical schema | Must | Thiết kế schema chung: timestamp, level, service, component, message, session/trace optional | LOG-UNIFY-001 | AI | Week 1 | P1.2 | Missing fields/format variation có handling contract. | Done
P1.4 | P1 · Data & Protocol | Normalisation | Must | Mask ID/IP/UUID/numbers; giữ raw message và optional Drain3 template | Normaliser | AI | Week 1 | P1.3 | Raw semantic text không bị mất; transform deterministic. | Done
P1.5 | P1 · Data & Protocol | Split | Must | Thiết kế chronological leave-one-architecture-out source/target folds | CS-SPLIT-001 | AI | Week 1 | P1.2 | Target architecture không xuất hiện trong source train của fold. | Done
P1.6 | P1 · Data & Protocol | Target buffer | Must | Định nghĩa target normal burn-in, contamination bound và readiness checks | ADAPT-INPUT-001 | Người nghiên cứu | Week 2 | P1.3; P1.5 | Không dùng target labels; buffer version/hash/provenance đầy đủ. | Done
P1.7 | P1 · Data & Protocol | Isolation audit | Must | Audit chronology, source-target leakage, duplicate và label isolation | LEAK-CS-001 | AI | Week 2 | P1.4; P1.5; P1.6 | Audit pass trước representation training; labels chỉ ở evaluation boundary. | Done
P1.8 | P1 · Data & Protocol | Freeze | Must | Freeze data/schema/fold config và reproducible commands | G0 receipt | AI + Người nghiên cứu | Week 2 | P1.7 | G0 Protocol Ready được ký; no empirical claims yet. | Done
P2.PRE | P2 · Representation & Experts | Base Model / Tokenizer / Revision Freeze | Must | Freeze metadata only: base/tokenizer IDs and exact commits, quantization/precision, context, PEFT/LoRA versions, license/access, GPU/budget, seeds, artifact naming and provenance. No model download; runtime smoke-load belongs to P2.1 preflight. | LLM-BASE-001 | Người nghiên cứu | Week 3 | P1.8 | All required metadata resolved and reviewed under configs/models/base-freeze-v1.yaml; immutable revisions, policy/lock hashes and access evidence recorded. No placeholder permits PASS. | Done
P2.1 | P2 · Representation & Experts | Semantic Expert | Must | Implement semantic self-supervision and scoring with independent LoRA-Semantic. Retain source alignment / domain-adversarial diagnostic as conditional REP-DG-001 with explicit disposition; no target inputs or anomaly labels. Require portable data and training notebook. | LORA-SEM-001; REP-DG-001 (conditional); EXP-SEM-001 | AI | Week 3 | P2.PRE | P2.PRE PASS before execution; independent adapter and scoring provenance, label-free source train/validation, semantic notebook and tests; REP-DG-001 conditional disposition recorded. | In progress
P2.2 | P2 · Representation & Experts | Sequence Reference Framework | Must | Retain separate LoRA-Sequence as reference candidate; ordered next-event/log objective, context evidence and boundary tests. No shared adapter weights/state; require portable data and training notebook. | LORA-SEQ-001; EXP-SEQ-001 | AI | Week 3 | P2.1 | Independent reference checkpoint/config; order, session/partition boundaries and six sequence controls testable; notebook and lineage complete. | Not started
P2.3 | P2 · Representation & Experts | Lightweight Sequence Expert | Must | Compare at least one substantially lighter explicit sequence architecture on the same contexts and budgets. Preregister resource criterion; no winner assumed. Require training notebook; reuse sequence view. | EXP-SEQ-LIGHT-001 | AI | Week 4 | P2.2 | Required lighter candidate evaluated under frozen resource criterion and shared contexts; all six sequence controls, cost/quality evidence and notebook; no unsupported winner claim. | Not started
P2.4 | P2 · Representation & Experts | GTAT Expert | Must | Freeze exact GTAT source and graph/temporal specification before training. Report coverage/abstain for missing fields. Structural-temporal role cannot silently replace sequence role; require graph view and training notebook. | EXP-GTAT-001 | AI | Week 4 | P2.3 | Exact graph source/spec/objective frozen; coverage and temporal expressiveness tested; missing topology yields unknown; notebook and lineage complete. | Not started
P2.5 | P2 · Representation & Experts | Common Evidence Contract | Must | Validate common evidence across all four candidates; raw score, uncertainty/unknown, coverage, record IDs and version lineage. Phase-2 calibrated score remains null; reject missing provenance. | EVID-CS-001 | AI | Week 4 | P2.4 | All four candidate outputs validate common contract; unknown is explicit; no calibration, fabricated certainty or missing version/coverage. | Not started
P2.6 | P2 · Representation & Experts | Expert Diversity / Scientific Evaluation | Must | Own source-held-out diversity diagnostics and sequence controls for all candidates. No target inputs or adaptive fusion. Source-label metrics remain blocked pending explicit evaluation permission; no fabricated metrics. | P2-DIVERSITY-001 (G2 prep) | Người nghiên cứu | Week 4 | P2.5 | Versioned source diagnostics, redundancy and resource comparison; report unsupported capability. C2 blocks supervised metrics and completion evidence depending on them; no gate fitting. | Not started
P2.7 | P2 · Representation & Experts | Final Phase-2 Freeze | Must | Freeze candidate dispositions, retained reference artifacts, common interface and reproducibility package. Assemble G2 evidence for researcher review; no automatic gate pass or Phase-3 activation. | P2-FREEZE-001 | Người nghiên cứu | Week 4 | P2.6 | P2.6 complete; source-label/capability issues resolved for required evidence; reference artifacts retained; researcher G2 review required; G2 remains NOT_PASSED until signed. | Not started
P3.1 | P3 · Adaptation & Fusion | Held-out check | Must | Receive P2.6 diversity evidence and P2.7 freeze package; verify G2 before Phase-3 integration, without rerunning or owning Phase-2 evaluation. | G2 handoff verification | Người nghiên cứu | Week 5 | P2.7 | P2.6 evidence hashes and researcher G2 signature verified; Phase 3 remains disabled before approval. | Waiting researcher
P3.2 | P3 · Adaptation & Fusion | Target memory | Must | Xây normal prototype/memory và graph/sequence statistics từ target burn-in | ADAPT-MEM-001 | AI | Week 5 | P1.6; P2.7 | Memory only uses approved unlabeled buffer; hash/version recorded. | Not started
P3.3 | P3 · Adaptation & Fusion | Calibration | Must | Calibrate Llama-A, Llama-B và GTAT score bằng target-normal quantile | CAL-CS-001 | AI | Week 5 | P3.2 | Score scales comparable without target labels. | Not started
P3.4 | P3 · Adaptation & Fusion | Drift | Must | Đo domain drift, buffer coverage và GTAT topology coverage | DRIFT-CS-001 | AI | Week 5 | P3.2 | Drift metric has baseline and no silent recalibration. | Not started
P3.5 | P3 · Adaptation & Fusion | Uncertainty | Must | Định nghĩa confidence/uncertainty cho từng expert và abstain criterion | UNC-CS-001 | AI | Week 5 | P2.5; P3.3 | Unknown/review is first-class output, not forced anomaly label. | Not started
P3.6 | P3 · Adaptation & Fusion | Fusion baseline | Must | Cài strongest-single, Transformer Encoder và Isolation Forest/equal-weight comparator | FUS-BASE-001 | AI | Week 6 | P3.3 | Không learned target weights; old models remain explicit baselines. | Not started
P3.7 | P3 · Adaptation & Fusion | Adaptive gate | Conditional | Meta-train MLP 8→32→16→3 Softmax on leave-one-architecture-out episodes | FUS-GATE-001 | AI + Người nghiên cứu | Week 6 | P3.4; P3.5; P3.6 | Gate uses drift/uncertainty/context; not target labels. | Not started
P3.8 | P3 · Adaptation & Fusion | Complementarity + explanation | Must | Kiểm tra diversity và xuất top expert, weight, evidence, localisation/abstain reason | G3 evidence + EXPL-CS-001 | AI | Week 6 | P3.1; P3.6; P3.7 | Gate chỉ mở nếu diversity/stability evidence đạt; alert explanation contract pass. | Not started
P4.1 | P4 · Cross-System Validation | LOAO protocol | Must | Freeze held-out architecture folds, target buffer và selection policy | G4 prep | Người nghiên cứu | Week 7 | P3.8 | No random mixed-domain split; no post-hoc target tuning. | Waiting researcher
P4.2 | P4 · Cross-System Validation | Core evaluation | Must | Run chronological target evaluation for every held-out architecture | EVAL-CS-001 | Người nghiên cứu | Week 7 | P4.1 | Per-target AP/PR-AUC, AUROC, FAR, TTD, latency and CI traceable. | Waiting researcher
P4.3 | P4 · Cross-System Validation | Ablation | Must | Remove LoRA-A, LoRA-B, GTAT, adaptation and gate one at a time | ABL-CS-001 | AI + Người nghiên cứu | Week 7 | P4.2 | Contribution claims follow paired/cluster uncertainty. | Not started
P4.4 | P4 · Cross-System Validation | Cold start | Must | Stress test short burn-in and previously unseen template/service | ROB-COLD-001 | AI + Người nghiên cứu | Week 7 | P4.2 | Report readiness threshold and failure modes. | Not started
P4.5 | P4 · Cross-System Validation | Contamination | Must | Stress test contaminated normal buffer and controlled drift | ROB-CONTAM-001 | AI + Người nghiên cứu | Week 8 | P4.2 | Quantify degradation; no hidden target labels. | Not started
P4.6 | P4 · Cross-System Validation | Reliability | Must | Audit dataset/model/gate/buffer hashes, seeds, commands and latency | REPRO-CS-001 | AI | Week 8 | P4.2; P4.3; P4.4; P4.5 | All reported metrics trace to immutable artifacts. | Not started
P4.7 | P4 · Cross-System Validation | Claims | Must | Build claim-to-evidence map and document limits/unknown cases | CLAIM-CS-001 | AI + Người nghiên cứu | Week 8 | P4.6 | No universal-generalisation claim beyond evaluated domains. | Not started
P4.8 | P4 · Cross-System Validation | Final report | Must | Write thesis/report and handoff reproducible model package | REPORT-CS-001 | AI + Người nghiên cứu | Week 8 | P4.7 | Architecture, protocol, results, limitations and source links complete. | Not started

## Gates
UNLOCK GATES
A gate can be marked passed only with named evidence. Gates protect target-label isolation and credible cross-system claims.
Gate | Decision | Required evidence | Forbidden action before pass | Owner | Depends on | Status | Evidence link / note
G0 | Protocol Ready | At least 3 source architectures; schema, LODO split and label-isolation audit | Representation or target adaptation training | Researcher | P1.1–P1.8 | Passed | data/processed/protocol/G0-receipt.json
G1 | Adaptation Ready | Normal burn-in assumption, contamination bound, local-memory/calibration tests | Use target labels or silent recalibration | Researcher | P1.6; P3.2–P3.5 | Not passed | —
G2 | Expert Diversity | Held-out source results, disagreement/double-fault and evidence contract | Adaptive learned fusion | Researcher | P2.PRE; P2.1–P2.7 | Not passed | —
G3 | Fusion Justified | MLP gate vs single/equal/Transformer/IF baselines; FAR/stability checks | Final claim that fusion is superior | Researcher | P3.6–P3.8 | Not passed | —
G4 | Final Evaluation | Data/model/buffer/gate/threshold freeze and reproducibility receipt | Post-hoc tuning or universal-generalisation claim | Researcher | P4.1–P4.7 | Not passed | —

## Traceability
TRACEABILITY — RESEARCH QUESTIONS TO EVIDENCE
Every result must identify the target architecture, target-buffer version, model/gate version and immutable evaluation run.
RQ | Question | Primary metric | Unit of evaluation | Task IDs | Required evidence | Claim allowed | Claim forbidden | Owner | Status
RQ1 | Can a representation generalise across log syntaxes? | Per-target AP/PR-AUC + CI | held-out architecture | P1–P2 | LOAO splits + expert runs | Generalises across evaluated targets | Universal generalisation | AI + Researcher | Planned
RQ2 | Can target normal-only adaptation calibrate unseen systems? | FAR, calibration, abstention | target normal buffer + later logs | P1.6; P3.2–P3.5 | buffer hash + calibration run | Adapts without target labels | Works before sufficient normal buffer | AI + Researcher | Planned
RQ3 | Does adaptive fusion add value? | AP/FAR vs Llama/GTAT/single/equal/legacy baselines | architecture × fold | P3.6–P3.8; P4.3 | paired result + ablation | Stable gain on evaluated domains | Gain from arbitrary score sum | AI + Researcher | Planned
RQ4 | What happens under drift/cold start/contamination? | degradation + latency | robustness scenario | P4.4–P4.5 | scenario bundles | Known operating envelope | Robust to all drift | AI + Researcher | Planned
RQ5 | Are conclusions reproducible? | hash/config/seed audit | final bundle | P4.6–P4.8 | repro + claim map | Traceable conclusion | Unbacked metric/claim | AI + Researcher | Planned

## Research Sources
RESEARCH SOURCES — VERIFIED CITATION KEYS
Use S# tags in Task Playbooks. These sources justify design choices only; none is evidence that the proposed model already works.
Key | Paper / year | Type | Contribution used in plan | Use boundary | URL / DOI | Status
S1 | Loghub — Zhu et al. (2020) | arXiv / Loghub | Dataset inventory, provenance, architecture diversity | Dataset availability only; do not infer labels or licences without checking registry | https://arxiv.org/abs/2008.06448 | Verified
S2 | Drain — He et al. (2017) | IEEE ICWS | Optional parser/template field; retain raw logs | Parser support only; not an anomaly model | https://doi.org/10.1109/ICWS.2017.13 | Verified
S3 | LogDLR — Liu et al. (2025) | IEEE TDSC | Cross-system, domain-invariant representation, adversarial branch | Architecture inspiration; no performance transferred to this project | https://ieeexplore.ieee.org/abstract/document/10910212/ | Verified
S4 | ZeroLog — Zhao et al. (2025) | arXiv preprint | Zero-label target protocol and meta-learning direction | Preprint; use as research design reference, not established fact | https://arxiv.org/abs/2511.05862 | Verified
S5 | LogLLaMA — Yang & Harris (2025) | arXiv preprint | LLaMA direction and next-log modeling | Uses LLaMA2; does not validate this project’s Llama-3.1 design | https://arxiv.org/abs/2503.14849 | Verified
S6 | LogGT — Wang et al. (2024) | Expert Systems with Applications | Event/component/time graph and GTAT direction | Architecture reference; results are not copied into this project | https://doi.org/10.1016/j.eswa.2024.124082 | Verified
S7 | LoRA — Hu et al. (2021) | arXiv | Frozen base + separate low-rank adapters | Does not establish task-specific performance | https://arxiv.org/abs/2106.09685 | Verified
S8 | DANN — Ganin et al. (2015) | JMLR / arXiv | Optional adversarial domain adaptation | Use only after diagnostic + ablation; not assumed beneficial | https://arxiv.org/abs/1505.07818 | Verified
S9 | SelectiveNet — Geifman & El-Yaniv (2019) | ICML / PMLR | Abstention and risk–coverage framing | Does not set an automatic threshold for this project | https://proceedings.mlr.press/v97/geifman19a.html | Verified
S10 | Isolation Forest — Liu et al. (2008) | IEEE ICDM | Explicit anomaly baseline | Baseline only; feature/budget policy must be declared locally | https://doi.org/10.1109/ICDM.2008.17 | Verified
S11 | Meta Llama 3.1 (2024) | Meta official release | Base-model revision, license and tokenizer provenance | Official model information; still require project-specific evaluation | https://ai.meta.com/blog/meta-llama-3-1/ | Verified

## Task Playbooks
TASK PLAYBOOKS — CÁCH LÀM & DEFINITION OF DONE
Mỗi dòng là protocol thực hiện dự kiến, bằng chứng cần lưu và điều kiện đóng task. Tag S# trỏ tới sheet Research Sources; trích dẫn hướng dẫn thiết kế, không phải kết quả thực nghiệm.
Task ID | Cách làm có kiểm soát | Evidence bắt buộc | Definition of Done có thể kiểm chứng | Trích dẫn
P1.1 | 1) Viết scope memo có định nghĩa “architecture” theo hệ thống/nguồn log, không theo EventID. 2) Vẽ một fold: source architectures → target architecture → target buffer → evaluation. 3) Liệt kê trường dữ liệu bị cấm ở từng bước (đặc biệt target labels). | Scope memo, sơ đồ fold, danh sách trường bị cấm, người duyệt. | Memo nêu rõ target chưa thấy; adaptation không đọc target label; sơ đồ và policy được reviewer ký. Không tuyên bố hiệu năng. | S3; S4
P1.2 | 1) Chọn tối thiểu 3 architecture khác họ hệ thống khi khả thi. 2) Với từng bộ dữ liệu, ghi URL/giấy phép, số dòng, timestamp, nhãn, đơn vị session và SHA-256. 3) Chỉ đưa dữ liệu có provenance vào registry. | dataset_registry.csv + LICENSE/URL + checksum + metadata snapshot. | Mọi dataset có provenance, khả năng dùng nhãn và phạm vi thời gian; mỗi fold có target held-out xác định trước. | S1; S3; S4
P1.3 | 1) Lập data dictionary cho timestamp, level, service, component, raw_message, session/trace và missingness. 2) Chuyển từng nguồn vào schema; giữ source_row_id bất biến. 3) Viết unit test cho timezone, null, parse failure và type. | LOG-UNIFY-001, mapping per source, test report. | Schema versioned; 100% trường required/nullable có quy tắc; lỗi parse được đếm và không bị im lặng loại bỏ. | S1; S6
P1.4 | 1) Giữ raw_message bất biến; tạo normalized_message ở cột mới. 2) Mask ID/IP/UUID/số bằng rule versioned, có ngoại lệ để không xóa token nghiệp vụ. 3) Chạy transform hai lần và so hash; Drain3 template chỉ là trường phụ trợ. | Rule file, golden cases, before/after sample, deterministic hash. | Raw text còn truy xuất được; transform deterministic; tỷ lệ match/rơi log báo cáo; template không thay raw text. | S2; S6
P1.5 | 1) Chọn target architecture trước khi train và tách toàn bộ target khỏi source. 2) Trong mỗi architecture, split theo thời gian: train/normal-buffer/eval theo chronology. 3) Xuất manifest gồm IDs, time boundary, hashes và seed. | CS-SPLIT-001 manifests, overlap scan, fold diagram. | Không có target architecture trong source train; không có thời điểm evaluation đi vào train/buffer; manifest tái tạo cùng split. | S3; S4; S6
P1.6 | 1) Định nghĩa burn-in duration, sampling rule, contamination assumption/bound và readiness minima trước khi xem kết quả. 2) Lưu hash và provenance buffer. 3) Gắn cờ “not ready/unknown” nếu thiếu coverage; không suy từ target labels. | ADAPT-INPUT-001, buffer manifest, readiness checklist. | Buffer không chứa cột/lookup target label; assumptions, hash, duration và rejection rule có chữ ký researcher. | S4; S9
P1.7 | 1) Kiểm tra duplicate bằng hash raw/normalized; kiểm tra session/time overlap. 2) Quét code/config bảo đảm labels chỉ mở ở evaluation boundary. 3) Lập danh sách exception có lý do và người phê duyệt. | LEAK-CS-001 with duplicate, overlap and label-access reports. | Leakage audit pass hoặc exception được resolve; không train/tune/calibrate bằng target label; report tái chạy được từ manifest. | S3; S4
P1.8 | 1) Khóa schema, normalizer, dataset registry, split manifest và env lockfile. 2) Ghi command tái tạo từng artifact và SHA-256. 3) Gate review chỉ xác nhận protocol, không đánh giá model. | G0 receipt, version manifest, reproducible command list. | G0 được ký; mọi input/config hashable; các task representation/adaptation chưa được chạy trước G0. | S1; S4
P2.PRE | Freeze metadata only: base/tokenizer IDs and exact commits, quantization/precision, context, PEFT/LoRA versions, license/access, GPU/budget, seeds, artifact naming and provenance. No model download; runtime smoke-load belongs to P2.1 preflight. | LLM-BASE-001 | All required metadata resolved and reviewed under configs/models/base-freeze-v1.yaml; immutable revisions, policy/lock hashes and access evidence recorded. No placeholder permits PASS. | S11; S7
P2.1 | Implement semantic self-supervision and scoring with independent LoRA-Semantic. Retain source alignment / domain-adversarial diagnostic as conditional REP-DG-001 with explicit disposition; no target inputs or anomaly labels. Require portable data and training notebook. | LORA-SEM-001; REP-DG-001 (conditional); EXP-SEM-001 | P2.PRE PASS before execution; independent adapter and scoring provenance, label-free source train/validation, semantic notebook and tests; REP-DG-001 conditional disposition recorded. | S7; S5; S11; S3; S8; S4
P2.2 | Retain separate LoRA-Sequence as reference candidate; ordered next-event/log objective, context evidence and boundary tests. No shared adapter weights/state; require portable data and training notebook. | LORA-SEQ-001; EXP-SEQ-001 | Independent reference checkpoint/config; order, session/partition boundaries and six sequence controls testable; notebook and lineage complete. | S5; S7; S11; S4
P2.3 | Compare at least one substantially lighter explicit sequence architecture on the same contexts and budgets. Preregister resource criterion; no winner assumed. Require training notebook; reuse sequence view. | EXP-SEQ-LIGHT-001 | Required lighter candidate evaluated under frozen resource criterion and shared contexts; all six sequence controls, cost/quality evidence and notebook; no unsupported winner claim. | S5; S4
P2.4 | Freeze exact GTAT source and graph/temporal specification before training. Report coverage/abstain for missing fields. Structural-temporal role cannot silently replace sequence role; require graph view and training notebook. | EXP-GTAT-001 | Exact graph source/spec/objective frozen; coverage and temporal expressiveness tested; missing topology yields unknown; notebook and lineage complete. | S6
P2.5 | Validate common evidence across all four candidates; raw score, uncertainty/unknown, coverage, record IDs and version lineage. Phase-2 calibrated score remains null; reject missing provenance. | EVID-CS-001 | All four candidate outputs validate common contract; unknown is explicit; no calibration, fabricated certainty or missing version/coverage. | S5; S6; S9
P2.6 | Own source-held-out diversity diagnostics and sequence controls for all candidates. No target inputs or adaptive fusion. Source-label metrics remain blocked pending explicit evaluation permission; no fabricated metrics. | P2-DIVERSITY-001 (G2 prep) | Versioned source diagnostics, redundancy and resource comparison; report unsupported capability. C2 blocks supervised metrics and completion evidence depending on them; no gate fitting. | S3; S6
P2.7 | Freeze candidate dispositions, retained reference artifacts, common interface and reproducibility package. Assemble G2 evidence for researcher review; no automatic gate pass or Phase-3 activation. | P2-FREEZE-001 | P2.6 complete; source-label/capability issues resolved for required evidence; reference artifacts retained; researcher G2 review required; G2 remains NOT_PASSED until signed. | S3; S6; S9
P3.1 | Verify P2.6 diagnostic artifacts and P2.7 package hashes; confirm researcher G2 signature before integration. Do not duplicate source evaluation or use target labels for tuning. | P2.6/P2.7 evidence references and G2 handoff verification. | Existing diversity evidence verified, G2 signed and Phase-3 execution separately authorized; no new evaluation or superiority claim. | S3; S6
P3.2 | 1) Từ burn-in đã duyệt, xây prototype embedding, transition counts và graph statistics. 2) Tách memory key theo target/buffer hash. 3) Đóng băng memory trước chronological evaluation. | ADAPT-MEM-001 memory artifact, source buffer hash, creation log. | Memory chỉ đọc buffer đã approved; key chứa target+buffer hash; evaluation logs không làm thay đổi memory. | S4; S6
P3.3 | 1) Tính quantiles trên normal buffer cho từng expert; chọn rule chuyển score trước evaluation. 2) Lưu quantile values, sample count và buffer hash. 3) So unit/scale scores sau calibration nhưng không chọn threshold bằng target labels. | CAL-CS-001 calibration table, config, sanity plots. | Mỗi expert có scale documented; calibration artifact được freeze; không có access target label hay post-hoc threshold change. | S4; S9
P3.4 | 1) Predefine drift statistic giữa source/buffer và online coverage statistic. 2) Log baseline/ref distribution cùng version. 3) Khi vượt threshold, emit drift/review state; không tự recalibrate âm thầm. | DRIFT-CS-001 metric spec, baseline stats, threshold config. | Metric, reference data và threshold versioned; output lý giải được drift/coverage; recalibration phải tạo artifact mới. | S3; S6
P3.5 | 1) Chuẩn hóa uncertainty của từng expert và coverage. 2) Chọn abstain/review rule trước final evaluation. 3) Báo cáo risk–coverage/abstention rate cùng scores. | UNC-CS-001 uncertainty spec, abstain rule, example outputs. | Unknown/review là outcome hợp lệ; rule versioned và testable; không ép low-coverage record thành normal/anomaly. | S9
P3.6 | 1) Khóa baselines: strongest single, equal-weight, Transformer Encoder và Isolation Forest. 2) Dùng cùng fold, input access, time/budget policy. 3) Xuất configs/predictions bằng common evidence schema. | FUS-BASE-001 baseline configs, budget table, predictions. | Không có learned target weight trong baseline; baseline artifacts có cùng provenance; comparison eligibility được ghi rõ. | S10; S5
P3.7 | 1) Meta-train gate MLP 8→32→16→3 Softmax chỉ trên source LOAO episodes. 2) Input feature gồm drift/uncertainty/coverage/context đã định nghĩa; target label bị excluded. 3) Freeze gate before target evaluation; report gate vs equal/single. | FUS-GATE-001 episode manifest, gate config, input feature schema. | Gate training never reads target labels; feature list/version and weights archived; target inference uses frozen gate. | S4; S6; S9
P3.8 | 1) Đo complementarity (disagreement, correlation, double-fault) trong held-out source. 2) Chỉ unlock gate nếu tiêu chí diversity/stability predeclared đạt. 3) Với mỗi alert, xuất expert weights, evidence, localisation hoặc abstain reason. | G3 evidence, EXPL-CS-001, complementarity tables, alert examples. | Có bằng chứng expert không trùng lặp vô nghĩa; gate decision có receipt; mọi alert/review có explanation contract pass. | S6; S9
P4.1 | 1) Freeze folds, target buffers, metrics, selection rule và seed trước full run. 2) Đăng ký thứ tự run/chính sách xử lý failure. 3) Cấm post-hoc target tuning; mọi thay đổi tạo protocol version mới. | G4 prep, frozen evaluation manifest, run registry. | Protocol signed; target architecture, buffer và selection policy immutable; no random mixed-domain split. | S3; S4; S6
P4.2 | 1) Chạy chronological evaluation cho từng held-out target với model đã freeze. 2) Tính PR-AUC/AP, AUROC, FAR, time-to-detect, latency; bootstrap CI theo unit predeclared. 3) Lưu per-target predictions và metric script version. | EVAL-CS-001 predictions, metrics tables, CI config, runtime logs. | Mỗi metric trace tới prediction IDs; time order được giữ; CI unit/resampling rule stated; không gộp che mất per-target result. | S3; S4; S6
P4.3 | 1) Tháo đúng một thành phần/biến thể mỗi run (LoRA-A, LoRA-B, GTAT, adaptation, gate). 2) Giữ folds/seeds/budget như full model. 3) Báo cáo paired per-target deltas và uncertainty, không chỉ best run. | ABL-CS-001 ablation matrix, paired predictions, delta/CI table. | Mỗi claim thành phần có paired artifact; không đổi nhiều yếu tố cùng lần; negative/null result được giữ. | S5; S6; S7
P4.4 | 1) Predefine burn-in lengths và unseen service/template scenarios. 2) Chạy evaluation mà không sửa model sau từng scenario. 3) Report readiness threshold, coverage và failure mode. | ROB-COLD-001 scenario manifest, curves/tables, failure log. | Kết quả phân theo buffer length/scenario; threshold không chọn sau khi xem target labels; unknown cases được nêu. | S4; S9
P4.5 | 1) Định nghĩa controlled contamination/drift scenario và tỷ lệ trước run. 2) Tạo scenario bundle riêng, hashable; không để model đọc label để làm sạch. 3) Đo degradation so với clean buffer và report all settings. | ROB-CONTAM-001 scenario generator/config, paired results, degradation table. | Tỷ lệ/seed contamination traceable; không hidden target-label cleanup; degradation và giới hạn được công bố. | S4; S9
P4.6 | 1) Lập manifest dataset/model/adapter/gate/buffer/threshold hashes, seed và command. 2) Re-run một fold từ manifest trong clean environment. 3) So hash/metric tolerance và lưu latency hardware context. | REPRO-CS-001 full manifest, rerun log, comparison receipt. | Mọi metric có immutable inputs + code revision; rerun receipt pass hoặc discrepancy giải thích; không có result mồ côi. | S1; S7; S11
P4.7 | 1) Với mỗi claim, link trực tiếp artifact, fold, metric và CI. 2) Viết giới hạn: evaluated architectures, burn-in assumptions, drift/contamination, abstention. 3) Xóa/sửa claim không có evidence bundle. | CLAIM-CS-001 claim–evidence map, limitations checklist. | Không có claim universal/generalisation ngoài phạm vi evaluated; mọi số liệu truy ngược được; limitations có trong report. | S3; S4; S9
P4.8 | 1) Viết phương pháp theo protocol frozen; tách rõ planned method và empirical finding. 2) Đưa tables per-target, ablation, robustness, reproducibility và source links. 3) Bundle code/config/models theo license và handoff readme. | REPORT-CS-001 report, reproducibility bundle, citations and handoff README. | Report có architecture, protocol, results/CI, limitations và citations; bundle mở được từ README; không claim kết quả chưa chạy. | S1; S3; S4; S5; S6; S7; S9; S11